Plan of Operation Sample Table for One Activity – Provide a short narrative and a Table for each activity with the Objectives and Outcomes (use this format for the table)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Direct Academic Services to ABC High School Students** | | | | | | |
| **Objective:** 12th grade students will be able to demonstrate a greater understanding of the opportunities available for financial assistance for college attendance  **Projected** **Outcome:** The project expects 95% of the 12th grade students to participate in a workplace readiness and youth employment program by the end of the school year. | | | | | | |
| **Activity Description** | **Implementation Process** | **Activity Date** | **Expected Participants, Per Session** | **Evaluation Plan** | **Date (s)** | **Person (s) Responsible** |
| Remedial Classes | 1. Hold information session for parents and students 2. Identify students who need remediation 3. Work with students to complete remediation courses. 4. Follow-up with students to compare PARCC assessment and school unit assessment scores | Fall 2019  Spring 2020  Summer 2020 | 40  (260 total) | 1. Monitor student progress on course exams, assignments, and compare to pre-test baseline score.    2. Student self-report on remedial class experience  3. Track students who complete remedial class during sessions and on PARCC assessments | Planning  10/2019 thru  12/2019, Ongoing  Recruitment Registration  12/2019 thru 2/2020  Classes  \*6/2019 to 8/2019 and  \*9/2019 thru 10/2019 | 1. August Brown, project director  2. Aaron Jupiter,  GEAR UP SCHOOL coordinator  3. June Stars, project evaluator |